## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
0 | 0 | Project initialization |  | - | witts5 | very high | 1 | 1 | 1 | done
1 | 0 | Project analysis | analyse use cases, target users and requirements | - | witts5 | high | 8 | 12 | 8 | WIP (50%)
2 | 1 | Framework evaluation | find php framework for the project | - | zimmm14 | very high | 4 | 8 | 8 | done
3 | 1 | Database Model | engineer database model | - | witts5 | medium | 4 | 4 | 4 | done
4 | 1 | Design Prototype | create a prototype for the design | HTML / CSS | rytzr1 | medium | 4 | 4 | 4 | done
5 | 2 | Install framework | install framework on Mac | OS | zimmm14 | very high | 8 | 8 | 8 | done
6 | 2 | Install framework | install framework on Windows | OS | witts5 | very high | 8 | 12 | 12 | done
7 | 2 | Install framework | install framework on Linux | OS | rytzr1 | very high | 8 | 16 | 16 | done
8 | 3 | Database Model | Implement database-model in SQL | SQL | witts5 | medium | 2 | 2 | 2 | done
9 | 3 | Framework installation | clear compatibility-problems of framework | OS | zimmm14, witts5, rytzr1 | very high | 4 | 4 | 4 | done
10 | 3 | Design implementation | realize design prototype | HTML / CSS | rytzr1 | high | 4 | 8 | 8 | done
11 | 4 | Database Model | Implement database-model in laravel | PHP | witts5 | high | 8 | 8 | 8 | done
12 | 4 | ORM | Implement model in eloquent from laravel | PHP | witts5, zimmm14 | high | 4 | 4 | 4 | done
13 | 4 | Tags-View | Implement Tag view | PHP / Angular | zimmm14 | high | 4 | 2 | 2 | done
14 | 4 | Things-View | Implement Things view | PHP / Angular | witts5 | high | 4 | 4 | 4 | done
15 | 5 | Fix Tag margin | Fix margin of the tag-hole | CSS | rytzr1 | medium | 1 |  |  | started
16 | 5 | Color hash for Tags | Implement Tag's color to have a color hashed from it's name | Angular / CSS | rytzr1 | medium | 2 |  |  | wait for start
17 | 5 | User Authentication | Protect UI from unauthenticated access | PHP / Angular / CSS | zimmm14 | high | 8 |  |  | started
18 | 6 | User registration | Build UI for register new User | PHP / Angular / CSS | zimmm14 | medium | 4 |  |  | wait for start
19 | 6 | User-resources | Update model that only resources of the actual user are displayed | PHP / SQL | witts5 | high | 2 |  |  | wait for start
20 | 6 | Note of resource | add Note-field to resources | PHP / Angular / CSS |  | very high |  |  |  | wait for start
21 |  | add/update Resource UI | add UI to create or update aresource | Angular / CSS |  | very high |  |  |  | wait for start
22 |  | update resource tag | Implement to add a tag to an existing resource | PHP / Angular |  | very high |  |  |  | wait for start
23 |  | update resource tag | Implement to remove an existing tag from an existing resource | PHP / Angular |  | very high |  |  |  | wait for start
24 |  | update resource media | Implement to update the media from an existing resource | PHP / Angular |  | very high |  |  |  | wait for start
25 |  | update resource name | Implement update the name of an existing resource | PHP / Angular |  | very high |  |  |  | wait for start
26 |  | update resource note | Implement update the notes from an existing resource | PHP / Angular |  | very high |  |  |  | wait for start
27 |  | Search | Implement search for tags | PHP / Angular |  | very high |  |  |  | wait for start
28 |  | Tag filter | Implement tags filtering resources | PHP / Angular |  | high |  |  |  | wait for start
29 |  | Webservice consumption | implement wikipedia information for tags | PHP / Angular / REST |  | medium |  |  |  | wait for start
30 |  | Drag-n-Drop-edit | implement tags beeing added to thing by drag-&-drop | Angular / CSS |  | low |  |  |  | wait for start
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45